B  A  I  N  T  O  N     P  A  R  I  S  H     C  O  U  N  C  I  L

  
MINUTES OF THE MEETING HELD ON MONDAY 14th SEPTEMBER 2026 AT 7.00PM 
IN BAINTON VILLAGE HALL.

1. Present 
Cllr P Brierley Chairman (PB), Cllr D Walford Vice Chairman (DW), Cllr A Dodgson (AD), Cllr C Bays (CB), Cllr S Lowes (SL), Cllr P Metcalf (PM), Cllr S Brown (SB), Cllr G Johnson (GJ). Mr L Conneally, Clerk to the Council (LC) & 3 members of the public. 

Cllr P Brierley Chairman chaired the meeting. PB formally opened the meeting, welcoming all and thanked everyone present. 

2. Apologies for absence 
Ward Cllr M Lee, A member of the public was interested in joining the council but was ill at the last minute. 
	
3. Declarations of interest
None

4. Previous Minutes 
The minutes from 6th July 2026 were offered for approval and were unanimously agreed as a correct record. Motion proposed by PM and Seconded by CB; unanimous vote, all in favour.

5. Matters Arising
None - A number of matters were updated on the action log.
	A   C    T    I    O   N         L   O   G

	Topic
	Task
	Owner
	Status
	Update

	
	
	
	
	

	Village Green
	Currently the village green and village hall have no land registry info.  Look at creating a title for them under BPC
	PM
	Open
	The land donated from Allister Nelson has been finalised and awaiting updating to land registry. The remaining 2/3 of land is more straight forward and is also going through without concern.  
Currently waiting for second phase of land registry. PM added that everything is in hand with solicitors and is expected for completion by November 2026. It was also noted that the Village Hall land has been registered by the Village Hall Committee.

	Sewerage/drainage
	Inadequate sewerage system, require meeting with YW and ERYC
	PB/DW& LC
	Open
	*see main minutes under flood update

	Street lights
	Additional Street lights on Church Street 
	DW
	Open
	DW monitoring grants situation.
12/25 – New grants are available so DW will look into whether any are appropriate.

	New notice board
	Residents have requested that the village noticeboard be relocated to a more central site and also be more accessible to advertise village events.  Suggestion to approach Bainton Stop. 
	DW
	Open
	Manager welcoming of the idea and has agreed to speak with the owner.  Permission received in principle – ongoing.

Rather than solely moving to the notice board, it is agreed to replace the board also.





6. Parish Council Vacancy
	There is currently one vacancy on the Parish Council. PB noted this had been the case for a considerable amount of time. PB said we do have someone interested in the final slot and hopefully that will be filled soon, but is vacant as it stands.



7. Highway Matters 
i)  Village flood update
PB reported that a meeting had been held in the village on 17th August with representatives from Yorkshire Water and East Riding of Yorkshire Council (ERYC). Landowners with an interest in the affected areas were also involved, including Tom Megginsons, Alistair Nelson, the Beaumonts and the former and current owners of the Old Post Office property and adjacent field. The meeting considered potential measures to address the longstanding flooding and drainage issues within the village. It was explained that a joint bid is to be developed for more natural, non-construction-based flood alleviation measures in order to apply for Environment Agency funding. Potential options discussed included the creation of an attenuation area within the Old Post Office field, ensuring an effective connection from the sump to the dyke via South Lane, and improving the connection from the western end of the village to Wellsprings dyke. PB advised that the meeting had been constructive and included a walk around the village, allowing the representatives to see first-hand the areas of concern. Yorkshire Water advised that further work would also be required to ensure that foul water is appropriately separated from surface water. ERYC is also developing a flood warning system intended to provide advance warning when there is an increased risk of flooding. Improvements to drainage along Church Lane were also discussed. It was noted that when future highway works are undertaken, the existing drainage arrangements will be reviewed as part of those works. DW added that the meeting had lasted several hours and had involved a detailed discussion of the issues. Although the existing gully along South Lane is relatively shallow, it was considered that a sump could still potentially be installed to assist with the dispersal of surface water. DW further reported that the ERYC representative had sought permission for the possibility of installing a pipe from the Old Post Office site directly to Inglenook Dyke. It was agreed that the initial priority should be the proposed works associated with the Old Post Office site and using existing infrastructure.
DW considered the meeting to have been positive overall and also confirmed that the works to the pipe outside August House had now been completed.
DW said he felt that contact had now been established with the appropriate officers and that those involved appeared motivated to progress solutions to the village's flooding problems. 
SB asked which of the options discussed was considered the preferred solution. DW explained that there was unlikely to be one single measure capable of resolving the issues and that a combination of interventions would be required. PB added that the relevant authorities would initially consider more natural flood-management measures before progressing to more invasive construction works where necessary.
PM asked whether the timescale discussed meant that the proposed measures were now likely to progress during the following year. PB confirmed that, based on the discussions to date, this appeared likely.

ii) Road maintenance update 
PB highlighted that this was covered above.

iii) Green Lane closure order & downgrading 
It was noted that Cllr Lee was unable to attend the meeting. As members considered his input important to the discussion, it was agreed that the matter would be deferred for further consideration at the next Parish Council meeting when, it was hoped, Cllr Lee would be present. It was noted that the temporary closure order for Green Lane remained in place at the time of the meeting.

iv) Public Seating 
PB reported that a resident had raised concerns regarding a village bench which had deteriorated and was in a very poor condition. Due to its condition, the bench had subsequently been removed by an independent contractor. PB advised that the contractor had been asked to await further instruction while the Parish Council sought clarification from East Riding of Yorkshire Council (ERYC) as to whether it wished for the bench to be repaired or replaced. DW recalled that the benches had originally been provided by ERYC in approximately 1999, during his time as Parish Clerk. SB asked for an update regarding the condition and maintenance of the village bus shelter, noting that it was also in a poor state of repair, with exposed nails and areas where the timber had swollen. DW suggested that the Parish Council establish responsibility for the ongoing maintenance and repair of both the benches and the bus shelters. PB asked LC, upon receipt of a response from ERYC regarding the bench, to reply and also raise the Parish Council’s concerns regarding the condition of the bus shelters and seek clarification as to responsibility for their maintenance and repair.

v) Eastern Green Link Traffic
DW reported that construction-related traffic had been travelling through the village, in some instances at speed, which had raised concerns among residents. He advised that he had been in email correspondence with the contractors regarding the matter and was continuing to seek clarification and a response to the concerns raised. DW also reported that a number of trees along Green Lane had been felled during the course of the works. He advised that he also wants to establish whether there are plans to replace the trees, noting that they had originally been carefully planted by the village.

8. Communications & PR to the village
i) Bainton Beacon 
DW reported that the current format of the Bainton Beacon appeared to be working well and helping to maintain the publication in a healthy and sustainable position. It was therefore proposed that the eight-page format should continue for future editions. DW advised that he would investigate the possibility of using a higher-quality paper for printing, which could improve the durability and overall presentation of the publication, particularly when being handled and distributed by post. DW agreed to investigate the available options, including the associated costs, and report back on their financial viability and feasibility.

ii) Social committee
PM reported that a number of social events were planned for the coming months, including a village quiz night. Further details of the events would be communicated to residents in due course.

iii) Development funding update 
DW provided an update on the project, explaining that delays associated with the grant process had resulted in the building and groundworks not yet commencing. He noted that approximately 13 months had passed since the original quotation was received and, as a result, an updated cost for the groundworks had been agreed, representing an increase of £250.00. DW advised that the additional cost would need to be accommodated within the overall approved funding allocation. This would require a small reduction in expenditure on lower-priority items, such as play equipment, to ensure that the project remained within the approved budget. DW also reported that clarification had recently been received from East Riding of Yorkshire Council (ERYC) regarding the payment arrangements. Due to the administrative requirements of the grant scheme, the Parish Council is required to initially fund the relevant works and subsequently reclaim the expenditure from ERYC upon completion. ERYC had confirmed that grant monies could only be released once the relevant works had been completed. The required payment to the contractor had now been made and, as a result, the project was in a position to proceed with the groundworks.

9. Planning applications
DW reported that planning application 25/01214/PLF relating to Bainton Stop had been approved, subject to conditions. He explained ERYC planners have treated it as a large retail unit, rather than as a hospitality business and that conditions had been imposed regarding its operating hours. DW advised that the applicant had sought Sunday opening hours of 9.00am to 6.00pm, Sunday being an important trading day for the business. The approved Sunday operating hours were currently restricted to 10.00am to 4.00pm. It was understood that the applicant intended to appeal this condition. DW invited members to express their views on the matter. SL considered that the permitted Sunday opening hours should be extended to allow the business to maximise its trading opportunities. GJ raised the issue of motorcycle parking. DW confirmed that motorcycles were now required to park within the side car park. PM noted that motorcycles and visiting motorcyclists had been a longstanding feature of the village for more than 20 years. SB expressed concern that there may be insufficient space within the side car park to accommodate the number of motorcycles visiting the premises. PM commented that Bainton Stop served as an important community hub and provided a significant benefit to residents and the village as a whole. He considered that, when assessing matters such as these, the wider benefits to the community should also be taken into account.
[bookmark: _GoBack]
10. Finance & Administration
Bank reconciliations circulated prior to the meeting. 
	Current account
	Reserve account
	Action fund

	£115.63
	£4899.08
	£0



i) Payments   	 	
No payments

11. Any other business


Elected Members
PB reported that a member of the public, who had expressed an intention to join the Parish Council, had raised concerns regarding excessive vehicle speeds on Middleton Road, close to their property. They requested that consideration be given to the installation of a speed camera at this location. PB explained that the Parish Council had, within the previous six months, sought to progress measures to address speeding concerns at this location, but the proposals had not received support from East Riding of Yorkshire Council (ERYC). PB suggested that a stronger evidence-based case should now be developed and submitted to ERYC in support of further measures to address vehicle speeds on Middleton Road.


Ward Councillors
None 


Members of the public
A member of the public stated that their preferred solution in relation to flood defence would be the installation of a new pipe across the field and expressed disappointment that this had not been pursued as the initial course of action. PB explained that the Parish Council was working with a large external organisation on the matter and, at this stage, was following the advice and proposed approach of the relevant authority. PM commented that the measures implemented to date may have reduced the risk of flooding; however, there had not yet been a period of sufficiently heavy rainfall to fully test their effectiveness. Another member of the public agreed with comments made by DW and expressed the view that the ERYC representative had not made sufficiently clear that the installation of a direct pipe was his principal objective. She felt that the strength of the case for this option had not been communicated as effectively as it could have been. PB committed to requesting a details breakdown of the funding request that should already have been submitted and then querying whether the direct pipe option could still be pursued.

12. Date of next meeting:  Monday 9th November 2026 at 19.00.
PB Thanked all council members and members of the public, before closing the meeting at 19.58.

